## Product Backlog
Product Backlog
| Project Name: | Chateau Project
| User Story or Feature (Functionality) |  |  | Estimate in Points | Acceptance Criteria | Rationale for Priortization | Other Notes | Sprint #
| As a | I/we want to | So that I/we can
| Painter | repaint the wrought iron gate | create a optical first impression | 10 | The frame and 30 iron bars has been painted | high | The front of the property is what gives prospective purchasers their first impression of it, making it a crucial factor. | 1
| Flooring Speacialist | upgrade the Marquise de Maillé's bedroom's flooring. | recreate the elegant ambiance of an 18th-century residence utilising prominent stamps on decorations and furnishings. | 75 | The new flooring has been installed | high | Because the worth of a house resides in its ancient decoration and surroundings, we aim to preserve its original and antique sentiments. | 1
| Electrician | resolve electrical issue with the light switch | utilize the lighting | 5 | The light switch are usable | high | Lighting is an important component that is necessary in every home, and having lighting at the Château improves the ambience. | 1
| Painter | complete the front façade painting of Chateau | provide buyers optical impact of property | 15 | the front facade is repainted | High |  | 1
| Cleaner | clean every windows | showcase the building's unique interior | 15 | The natural light enters the building interior | High |  | 1
| Designer | re-arrange furniture from the current configuration | provide more suitable options for buyers who do not want to buy it for run tours | 40 | Provide a range of configuration building can be used for i.e. run tours, museum, etc. | high | The house has a prospectus that includes other uses besides runtours that we wish to highlight. | 1
| Roofer | repair the chimney | assure that no major accidents takes place | 25 | There are no loose bricks in the chimney | high |  | 2
| Stair specialist | repair the exterior front stairs leading to the main door | prevent anyone from tripping on the stair steps. | 10 | The front stairs are repaired | high |  | 2
| carpenter | repair the main floor foyer | make the inside look appealing to buyers | 5 | The main foyer is repaired | high |  | 2
| blacksmith | remove the barriers in railings and doorway | assure prospective buyers that Chateau has potential beyond that of a tour group business | 5 | There are no barriers in the doorway or railing | high |  | 2
| Designer | improve the kitchen illumination | create a stunning kitchen interior | 30 | The kitchen appears cosy and well-lit. | medium |  | 2
| former Government Inspector | have the structural inspected by a government inspector | complete final legal paperwork for the sale | 15 | Approved inspection certificate is received | low |  | 2
| Roofer | repair shingles on the roof | prevent water leaking | 20 | The leak noted in the roof is fixed | low | Despite the fact that the leak is not letting water in, it should be fixed while it is still tiny because there is a potential that it will cause further harm. | 2
|  |  | Total estimation points | 270
Selected user stories (3)
| Painter | repaint the wrought iron gate | create a optical first impression | 10 | The wrought iron gate has been painted | high |  | 1
| Flooring Speacialist | upgrade the Marquise de Maillé's bedroom's flooring. | recreate the elegant ambiance of an 18th-century residence utilising prominent stamps on decorations and furnishings. | 75 | The new flooring has been installed | high |  | 1
| Electrician | resolve the light switch's electrical issue. | utilize the lighting | 5 | The light switch are usable | high |  | 1
|  |  | Total estimation points of selected user stories | 90
Note for estimate points
Estimate points are calculated on the basis of reference story point given on case

## DoD, Velocity, # of Sprints
Product Backlog
| Chateau Project | Velocity Calculations, show your math |  |  | Calculations for the # of Sprints Required to deliver all of the stories listed in the Product Backlog, show your math
| Defintions of Done (DoD) | Sprints | velocity for 1 week sprint | If sprint is 2 week long
| The paint has passed the designer review | 4 week ago | 80 | 160 |  | Total estimation point of the product backlog | 270
| Product owner acknowledges the upgraded flooring | 3 weeks ago | 120 | 240
| No defects are on electrical component | 2 weeks ago | 105 | 210 |  | Velocity for sprint 1 | 162
| The painting has been completed | 1 week ago | 19 | 38 |  | Velocity for sprint 2 | 136
| All the 120 windows are cleaned | Velocity of sprint | Average of last 3 sprints
| The furniture are all set according to the new arrangement layout | Velocity of sprint 1 | 162 |  |  | Total story point of 2 sprint | 298
| The firework and safety requirement passed |  |  |  |  | Number of Sprints required to complete backlog | 2
All the stairs are of uniform height and clean
Legal standard passed
Interior Designer standard passed
The railing and doorway are restored to their antique appearance.
The kitchen lightening meets the acceptence criteria
There are no leaks in the shingles
3 DOD for the 3 selected user stories
| The frame and 30 iron bars has been painted | Notes for sprint 1 velocity calculation
| Product owner acknowledges the upgraded flooring | Step 1 | Converted velocity of 1-week sprint to 2-week sprint velocity = Velocity of 1-week sprint * 2
| No defects are on electrical component | Step 2 | Calculated average velocity of last 3 sprints(2 week sprints) = ( 1 week ago sprint + 2 week ago sprint + 3 week ago sprint)/3
Notes for calculation for the sprints required to deliver all the stories listed in the product backlog
|  | Sprint 1 | Calculated average velocity of last 3 sprints(2 week sprints) = ( 1 week ago sprint + 2 week ago sprint + 3 week ago sprint)/3
|  | Sprint 2 | Calculated average velocity of last 3 sprints(2 week sprints) = ( Sprint 1 + 1 week ago sprint + 2 week ago sprint)/3