## Product Backlog
| Product Backlog |  | Enter your acceptance criteria, in your Sprint Review (demo) what would the PO be looking for before you can demo?
Priority | Story or Feature | Estimate in Points | Acceptance Criteria | Definition of DONE
1 | repaint the wrought iron gate | 10 | The wrought iron gate has been painted | The frame and 30 iron bars has been painted
2 | upgrade the Marquise de Maillé's bedroom's flooring. | 75 | The new flooring has been installed | Product owner acknowledges the upgraded flooring
3 | resolve the light switch's electrical issue. | 5 | The light switch are usable | No defects are on electrical component

## Sprint 1 Backlog
| Sprint 1 Goal | Repainting the iron gate, Upgrading the flooring, and Resolving electrical issue
|  | Enter your TOTAL team capacity in real minutes: 28800 minutes | The total capacity for a person for 2 week sprint is 4800 minutes. The number of team is considered as the highest resources required in all the features i.e. (2+2+2 = 6). Thus, the total team capacity = Total number of team (8) * Each person capacity in real minutes (4800), which gives 28800 minutes
Select the highest priority Features or Stories for your Sprint | Sprint 1 Backlog |  | Estimate each task in real time
| Story or Feature | Tasks | Estimate in Real (For number of resources mentioned in resources names |  |  | Resources Name
|  |  | Days | Hours | Minutes
| Repaint front gate | Protect the area around the fence | 1 | 8 | 480 | 2 painters
|  | Remove the rust | 1 | 8 | 480 | 2 painters
|  | Clean the fence | 0.5 | 4 | 240 | 2 painters
|  | Rinse with water | 0.5 | 4 | 240 | 1 painter
|  | Apply Primer | 1 | 8 | 480 | 2 painters
|  | Apply paint to metal surfaces | 2 | 16 | 960 | 2 painters
|  | Apply several coats of paints | 1 | 8 | 480 | 2 painters
|  | Total | 7 | 56 | 3360
| Upgrade the Marquise de Maillé's bedroom's flooring. | Acclimate the planks and preparation of the subfloor | 1.5 | 12 | 720 | 2 flooring specialist
|  | Preparing the door jambs | 0.5 | 4 | 240 | 1 flooring specialist
|  | Planning first and last row | 0.5 | 4 | 240 | 1 flooring specialist
|  | Cutting first and last floor | 0.5 | 4 | 240 | 1 flooring specialist
|  | Installing underlayment | 1.5 | 12 | 720 | 2 flooring specialist
|  | Install the flooring | 1.5 | 12 | 720 | 2 flooring specialist
|  | Total | 6 | 48 | 2880
| resolve the light switch's electrical issue. | Check the circuit breaker | 0.5 | 4 | 240 | One electrician
|  | Test the circuit breaker | 0.5 | 4 | 240 | 2 electrician
|  | Identify all the faulty light switch | 0.5 | 4 | 240 | 2 electrician
|  | Check the GFI (Ground Fault Interrupters) | 0.5 | 4 | 240 | 1 electrician
|  | Turn off all the light switch | 0.5 | 4 | 240 | 1 electrician
|  | Check for power | 0.5 | 4 | 240 | 1 electrician
|  | Replace the switch | 0.5 | 4 | 240 | 1 electrician
|  | Test the new switch | 0.5 | 4 | 240 | 1 electrician
|  | Total | 4 | 32 | 1920
Notes
A. Total working days in a week = 5 days
B. Total working hours in a day = 8 hours
C. Total minutes in an hour = 60 minutes
Total team capacity in a week = A*B*C = 2400 minutes
Each person capacity for 2 weeks = 2400 minutes * 2 = 4800 minutes

## Burndown chart
Burndown Chart
Backlog id | User stories | Initial Estimate (Minutes)) | Actual Task Completed (In Minutes) | [9 empty] | Remaining task (Minutes)
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| repaint the wrought iron gate | 3360 | 480 |  | 480 |  | 480 |  | 480 |  | 480 | 480 | 480
| upgrade the Marquise de Maillé's bedroom's flooring. | 2880 | 480 | 240 |  | 240 | 240 | 240 | 240 | 480 | 240 |  | 720
| resolve the light switch's electrical issue. | 1920 | 240 | 240 | 240 | 240 | 240 | 240 |  | 240
| Planned Minutes |  | 816 | 816 | 816 | 816 | 816 | 816 | 816 | 816 | 816 | 816
| Actual Minutes |  | 1200 | 480 | 720 | 480 | 960 | 480 | 720 | 720 | 720 | 480
| Remaining effort | 8160 | 6960 | 6480 | 5760 | 5280 | 4320 | 3840 | 3120 | 2400 | 1680 | 1200
| Ideal Trend | 8160 | 7344 | 6528 | 5712 | 4896 | 4080 | 3264 | 2448 | 1632 | 816 | 0
Acclimate the planks and preparation of the subfloor | Preparing the door jambs | Planning first and last row | Actual Task Completed (In Minutes) Day 1: Cutting first and last floor; Actual Task Completed (In Minutes) Day 2: Installing underlayment; Actual Task Completed (In Minutes) Day 3: Install first row; Actual Task Completed (In Minutes) Day 4: Install the remaining rows
900 | 225 | 450 | Actual Task Completed (In Minutes) Day 1: 450; Actual Task Completed (In Minutes) Day 2: 900; Actual Task Completed (In Minutes) Day 3: 420; Actual Task Completed (In Minutes) Day 4: 1350
2 | 0.5 | 1 | Actual Task Completed (In Minutes) Day 1: 1; Actual Task Completed (In Minutes) Day 2: 2; Actual Task Completed (In Minutes) Day 3: 1; Actual Task Completed (In Minutes) Day 4: 2
|  | color scheme checked and researched | Actual Task Completed (In Minutes) Day 1: 225; Actual Task Completed (In Minutes) Day 2: 0.5
|  | Wash the walls free of dust and grease. | Actual Task Completed (In Minutes) Day 1: 900; Actual Task Completed (In Minutes) Day 2: 2
|  | Cover the doors, windows, and fixtures with plastic sheets and painter’s tape. | Actual Task Completed (In Minutes) Day 1: 450; Actual Task Completed (In Minutes) Day 2: 1
|  | Fill the cracks, gaps, and holes with fillers | Actual Task Completed (In Minutes) Day 1: 900; Actual Task Completed (In Minutes) Day 2: 1.5
|  | Apply at least two coats of the new paint. | Actual Task Completed (In Minutes) Day 1: 1800; Actual Task Completed (In Minutes) Day 2: 3
|  | Total | Actual Task Completed (In Minutes) Day 1: 4275; Actual Task Completed (In Minutes) Day 2: 10
| Repaint front gate | Protect the area around the fence | Actual Task Completed (In Minutes) Day 1: 450; Actual Task Completed (In Minutes) Day 2: 1
|  | Remove the rust | Actual Task Completed (In Minutes) Day 1: 450; Actual Task Completed (In Minutes) Day 2: 1
|  | Clean the fence | Actual Task Completed (In Minutes) Day 1: 225; Actual Task Completed (In Minutes) Day 2: 0.5
|  | Rinse with water | Actual Task Completed (In Minutes) Day 1: 225; Actual Task Completed (In Minutes) Day 2: 0.5
|  | Apply Primer | Actual Task Completed (In Minutes) Day 1: 450; Actual Task Completed (In Minutes) Day 2: 1
|  | Apply paint to metal surfaces | Actual Task Completed (In Minutes) Day 1: 900; Actual Task Completed (In Minutes) Day 2: 2
|  | Apply several coats of paints | Actual Task Completed (In Minutes) Day 1: 450; Actual Task Completed (In Minutes) Day 2: 1
|  | Total | Actual Task Completed (In Minutes) Day 1: 1575; Actual Task Completed (In Minutes) Day 2: 7
| Upgrade the Marquise de Maillé's bedroom's flooring. | Acclimate the planks and preparation of the subfloor | Actual Task Completed (In Minutes) Day 1: 900; Actual Task Completed (In Minutes) Day 2: 2; Actual Task Completed (In Minutes) Day 3: 900
|  | Preparing the door jambs | Actual Task Completed (In Minutes) Day 1: 225; Actual Task Completed (In Minutes) Day 2: 0.5; Actual Task Completed (In Minutes) Day 3: 225
|  | Planning first and last row | Actual Task Completed (In Minutes) Day 1: 450; Actual Task Completed (In Minutes) Day 2: 1; Actual Task Completed (In Minutes) Day 3: 450
|  | Cutting first and last floor | Actual Task Completed (In Minutes) Day 1: 450; Actual Task Completed (In Minutes) Day 2: 1; Actual Task Completed (In Minutes) Day 3: 450
|  | Installing underlayment | Actual Task Completed (In Minutes) Day 1: 900; Actual Task Completed (In Minutes) Day 2: 2; Actual Task Completed (In Minutes) Day 3: 900
|  | Install first row | Actual Task Completed (In Minutes) Day 1: 420; Actual Task Completed (In Minutes) Day 2: 1; Actual Task Completed (In Minutes) Day 3: 450
|  | Install the remaining rows | Actual Task Completed (In Minutes) Day 1: 1350; Actual Task Completed (In Minutes) Day 2: 3; Actual Task Completed (In Minutes) Day 3: 1350; Actual Task Completed (In Minutes) Day 5: 3
|  | Total | Actual Task Completed (In Minutes) Day 1: 4695; Actual Task Completed (In Minutes) Day 2: 10.5; Actual Task Completed (In Minutes) Day 3: 4725; Actual Task Completed (In Minutes) Day 4: -30
Note: The data for the actual task completed was taken from task board completed each day.
Calculation
Planned Minutes for all cell
Total initial estimate / Number of days
Actual Minutes
sum of total task completed in each days i.e. E6:E8 and so on
Remaining Effort
For first cell, the total sum of the initial estimate
For cell 2 and after, the total of previous cell - actual minutes of respective column
Calculation of ideal trend
First first cell, total sum of the intial estimate .
For cell 2 and after, the total of previous cell - planned miinutes of the respective column