## Week 1
DAILY SCRUM MEETING
member | Question | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Painters | What did you do yesterday? |  | worked on Protect the area around the fence | Tested protected area around the fence | Working on removing rust | Tested if rust are removed according to requirement | Cleaned the fence and rised with water | tested if fence are cleaned and rised with water | Applied primer | Tested if primer are applied properly | Started applying paint to metal surface
| What are doing today? | Start working on Protect the area around the fence | Testing protected area around the fence | Started to remove the rust | Testing if rust are removed according to requirement | Cleaning the fence and rising with water | testing if fence are cleaned and rised with water | Apply Primer | Testing if primer was applied properly | Started applying paint to metal surface | Applying paint on metal surface
Is there anything blocking you? | bar: Day 1 to Day 10
Flooring Speacialist | What did you do yesterday? |  | worked on acclimate the planks and preparation of the subfloor | worked on acclimate the planks and preparation of the subfloor | Tested if sub-floor are prepared and planks are acclimated | Tested if door jambs are prepared properly | Planned first and last row | tested if planning of first and last row are done properly and Cutfirst and last floor | tested if first and last are cut properly | Started working on installation of underlayment | Installed underlayment
| What are doing today? | Starting working on acclimate the planks and preparation of the subfloor | working on acclimate the planks and preparation of the subfloor | Testing planks and preparation of the subfloor | Preparing the door jambs | Planning first and last row | testing if planning of first and last row are done properly and Cutting first and last floor | testing if first and last are cut properly | Installing underlayment | Installing underlayment | Testing installation of underlayment
Is there anything blocking you? | bar: Day 1 to Day 10
Electrician | What did you do yesterday? |  | worked on check the circuit breaker | worked on Test the circuit breaker and tested Check the circuit breaker | Identified all the faulty light switch and tested circuit breaker | Checked the GFI and tested if faulty lights are identified properly | Turned off all the light switch | Checked for power | tested if all pwer is checked and replaced the switch | Tested if all the required switches are replaced and tested the new switch
| What are doing today? | working on check the circuit breaker | start working on Test the circuit breaker and testing Check the circuit breaker | Identify all the faulty light switch and testing circuit breaker | Checking the GFI and testing if faulty lights are identified properly | Turn off all the light switch | Check for power | testing if all power is checked and replace the switch | Testing if all the required switches are replaced and start testing the new switch
Is there anything blocking you? | bar: Day 1 to Day 10

## Week 2
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Painters | What did you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you do yesterday?
What are doing today?
Is there anything blocking you?