## Slide 1: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 1
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, P
Apply Primer
480 min, P
Apply paint to metal surfaces.960 min,
P
Remove the rust
A
480 min, P
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, P
Cutting first and last floor
240 min, F.S
Rinse with water
A
240 min, P
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, E
Test the new switch
240 min, E

## Slide 2: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 2
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, P
Apply Primer
480 min, P
Apply paint to metal surfaces.960 min, P
Remove the rust
480 min, P
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, P
Cutting first and last floor
240 min, F.S
Rinse with water
240 min, P
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, E
Test the new switch
240 min, E

## Slide 3: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 3
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, P
Apply Primer
480 min, P
Apply paint to metal surfaces.960 min, P
Remove the rust
A
480 min, P
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, P
Cutting first and last floor
240 min, F.S
Rinse with water
240 min, P
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, E
Test the new switch
240 min, E

## Slide 4: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 4
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, P
Apply Primer
480 min, P
Apply paint to metal surfaces.960 min, P
Remove the rust
480 min, P
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, P
Cutting first and last floor
240 min, F.S
Rinse with water
240 min, P
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, E
Test the new switch
240 min, E

## Slide 5: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 5
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, P
Apply Primer
480 min, P
Apply paint to metal surfaces.960 min, P
Remove the rust
480 min, P
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, P
Cutting first and last floor
240 min, F.S
Rinse with water
240 min, P
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, E
Test the new switch
240 min, E

## Slide 6: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 6
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, P
Apply Primer
480 min, P
Apply paint to metal surfaces.960 min, P
Remove the rust
480 min, P
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, P
Cutting first and last floor
240 min, F.S
Rinse with water
240 min, P
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, E
Test the new switch
240 min, E

## Slide 7: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 7
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, P
Apply Primer
480 min, P
Apply paint to metal surfaces.960 min, P
Remove the rust
480 min, P
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, P
Cutting first and last floor
240 min, F.S
Rinse with water
240 min, P
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, E
Test the new switch
240 min, E

## Slide 8: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 8
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, P
Apply Primer
480 min, P
Apply paint to metal surfaces.960 min, P
Remove the rust
480 min, P
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, P
Cutting first and last floor
240 min, F.S
Rinse with water
240 min, P
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, E
Test the new switch
240 min, E

## Slide 9: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 9
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, P
Apply Primer
480 min, P
Apply paint to metal surfaces.960 min,
Remove the rust
480 min, P
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, P
Cutting first and last floor
240 min, F.S
Rinse with water
240 min, p
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, E
Test the new switch
240 min, E

## Slide 10: Project –Sprint 1
Stories | To Do | In Progress | Test | Done
Repaint front gate
Sprint 1 Day 10
Upgrade the Marquise de Maillé's bedroom's flooring.
Protect the area around the fence
480 min, p
Apply Primer
480 min, p
Apply paint to metal surfaces.960 min, P
Remove the rust
480 min, painter
Acclimate the planks and preparation of the subfloor
720 min, F.S
Clean the fence
240 min, p
Cutting first and last floor
240 min, F.S
Rinse with water
A
240 min, p
Apply several coats of paints.480 min, P
resolve the light switch's electrical issue.
Preparing the door jambs
240 min, F.S
Installing underlayment
720 min, F.S
Check the GFI
240 min, E
Install the flooring
720 min, F.S
Planning first and last row
240 min, F.S
Turn off all the light switch
240 min, E
Test the circuit breaker
240 min, E
Check the circuit breaker
240 min, E
Check for power
240 min, E
Identify all the faulty light switch
240 min, E
Replace the switch
240 min, Electrician
Test the new switch
240 min, E